## Meetings log sheet
NLP Project - Meetings Log Sheet
Team's Name
Meeting Number | Date | Start time | End time | Main points (bullets) | Any outstanding issues (really serious problems, not technical points you are solving) | Absent members
1 | 20/10/2024 | 17:00 | 18:15 | - project requirements - project plan | / | /
2 | 24/10/2024 | 18:30 | 19:30 | - checking data collection progress - methodology of data collection agreement - agreeing on LLMs to test | / | Yazid Sliman
3 | 29/10/2024 | 17:00 | 17:30 | - progress of data collection, - checkpoint - delivering tasks and setting deadlines | / | /
4 | 2024-07-11 | 18:30 | 19:55 | - discussed LLMs to be used - data cleaning - model primary training plan | / | /
5 | 2024-12-11 | 18:30 | 19:05 | -progress of the labeling - delivering last data file to be anotated - tasks reorganizing | / | /
6 | 2024-11-12 | 17:00 | 18:00 | - progress of data anotation - categories of annotation - chosing the model and fine tuning | / | Rym Selmani
7 | 17/12/2024 | 21:00 | 21:40 | - setting deadline for data annotation - deciding on the product delivery (a streamlit app) - setting deadline for model fine tuning - discussing labeling issues | / | /

## baraa
number of instances(labels) | number of Instances (bullying) | Date | Time